## ProductBacklog
PRODUCT BACKLOG
Batch 2018_2019
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | Student | Register Myself Using Poornima Mail Id | I Can Receive A Confirmation/Verification Mail
1 | SB1/US2 | Student | Receive A Confirmation Mail | I Can Access The Digital College System
1 | SB1/US3 | Student | Login Into The System Using Poornima Mail Id And Password | I Can View/Edit My Profile
1 | SB1/US4 | Student | View The type of test | I can view the type of test
1 | SB1/US5 | Student | View The profile | I can change the my profile
| SB1/US6 | Student | Modify The Account Password | I Can Keep My Account Secure
| SB1/US8 | Student | Give Feedback/Suggestions | The Way Of Working Of The Department Can Be Improved
| SB1/US9 | Student | demo test | I can give the demo test
| SB1/US10 | Student | select test module | I can select my test module
| SB1/US11 | Student | see the time clock | I can see exam test timer
| SB1/US12 | Student | select the tset | I Can give the test
| SB1/Us13 | Student | read the content and practise | I can read the content before test
| SB1/US15 | Student | submit the test | I Can view the result
| SB1/US16 | Student | View the leaderboard | I Can see my position in test
| SB1/US17 | Student | View My Result | I Can Analyze My Performance
| SB1/US18 | Student | view the solutions | I can see solution of question
| SB1/Us19 | Student | View no of students | I Can analyeze my position
| SB1/US20 | Student | See The time table and next date of exam | I Can set my time table
| SB1/US21 | Student | See The performance graph | I Can compare my parsent perfornce to past test
| SB1/US22 | Student | Download important notification | I Can Be see the notification ofline
| SB2/US1 | Student | Download answer key | I Can get solutio
| SB2/US2 | student | change the password | I can change the password
| SB2/US3 | Student | share the app | I can share the app
| SB2/US4 | student | rate the app | I can give the star rating
| SB2/US5 | student | Feedback From Students | I can give the feedback
| SB2/US6 | Student | about the app | I can read about the app
| SB2/US7 | Student | logout | I can signout the account
| SB2/US8 | Student | hobby | I can writte my hobby
| SB2/US9 | Student | post an mcq | I can post the mcq
| SB2/US10 | Student | update the app | I can update the app
| SB2/US11 | Student | ask the query | I can ask the query
| SB2/US12 | DBA | insert the question | I Can Insert the question in the datbase
| SB2/US13 | DBA | update the question | I Can update the new question in the datbase
| SB2/US14 | DBA | change the question | I Can change the question ar the real time
| SB2/US15 | DBA | timer | I can change the time of test
| SB2/US16 | DBA | delete the question | I Can Remove the question after test
| SB2/US17 | DBA | check the datbase like password\and mail id | I Can control tha user account
| SB2/US18 | DBA | publish the answer key | I Can give info about answers of question
| SB2/US19 | DBA | show result | I Can provide the result
| SB2/US20 | DBA | see feedback form | I can see the feedback form
| SB2/US21 | DBA | notification | I can provide the notification
| SB2/US22 | DBA | answer query | I Can control the queries
| SB3/US1 | DBA | the bug report | I can solve the bug of my app
| SB3/US2 | DBA | student hod feculty report | I can see the report of the student and faculty
| SB3/US3 | DBA | fill the requirment of the student | I can acess the recurment of faculty and hod about test and topc

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Digital College>
SB1/US1 | Register Myself Using Poornima Mail Id | SB1/D1/T1 | Designing the GUI | AKS | complete | 2018-08-20
|  | SB1/D1/T2 | validating user input at client level | Aks+DY | complete | 2018-08-22
|  | SB1/D1/T3 | validating user input at server | AKS+DY | complete | 2018-08-25
|  | SB1/D1/T4 | Testing of the module on localhost and then on server. | DY | complete | 2018-08-28
SB1/US2 | receive a confirmation mail | SB1/D2/T1 | designing of email | AKS | complete | 2018-09-02
|  | SB1/D2/T2 | study of mandrill app to send mail | AKS+DY | complete | 2018-09-06
|  | SB1/D2/T3 | send mail via coding | AKS+DY | complete | 2018-09-08
|  | SB1/D2/T4 | testing of module on local host | DY | complete | 2018-09-10
SB1/US3 | login into the system using poornima mail id | SB1/D3/T1 | designing the gui | AKS | incomplete | 2018-09-12
|  | SB1/D3/T2 | validiate the user input or client level | AKS+DY | incomplete | 2018-09-14
|  | SB1/D3/T3 | check user valid or not | AKS+DY | incomplete | 2018-09-16
|  | SB1/D3/T4 | testing of module on localhost | DY | incomplete | 2018-09-20
SB1/US6 | modifying the account password | SB1/D4/T1 | designing gui | AKS | incomplete | 2018-09-22
|  | SB1/D4/T2 | check user input at clicent level | AKS+DY | incomplete | 2018-09-24
|  | SB1/D4/T3 | check user input at server | AKS+DY | incomplete | 2018-09-26
|  | SB1/D4/T4 | testing of module on local host | DY | incomplete | 2018-09-20
SB1/US7 | view number of students | SB1/D5/T1 | designing gui | AKS | incomplete | 2018-10-02
|  | SB1/D5/T2 | check user valid or not | AKS+DY | incomplete | 2018-10-06
|  | SB1/D5/T3 | validate user input at clicent level | AKS+DY | incomplete | 2018-10-08
|  | SB1/D5/T4 | validate user input at server | DY | incomplete | 2018-10-10
SB1/US8 | give feedback suggestion | SB1/D6/T1 | designing gui | AKS | incomplete | 2018-10-12
|  | SB1/D6/T2 | vaidiate user input valid or not | AKS+DY | incomplete | 2018-10-14
|  | SB1/D6/T3 | validate user input at clicent level | AKS+DY | incomplete | 2018-10-15
|  | SB1/D6/T4 | validate user input at server | DY | incomplete | 2018-10-17
SB1/US9 | demo test | SB1/D7/T2 | designing the gui | AKS | incomplete | 2018-10-19
|  | SB1/D7/T3 | validate the user input or clicent | AKS+DY | incomplete | 2018-10-20
|  | SB1/D7/T4 | validate the user input or server | DY | incomplete | 2018-10-21
SB1/US10 | select test module | SB1/D8/T1 | designing the gui | AKS+DY | incomplete | 2018-10-22
|  | SB1/D8/T2 | validate the user inout at clicent | AKS | incomplete | 2018-10-24
|  | SB1/D8/T3 | validate the user at server | DY | incomplete | 2018-10-26
|  | SB1/D8/T4 | testing the module on localhost | AKS+DY | incomplete | 2018-10-28
SB1/US11 | see the time clock | SB1/D9/T1 | designing the gui | AKS | incomplete | 2018-10-30
|  | SB1/D9/T2 | validate the user input at clicent level | DY | incomplete | 2018-11-01
|  | SB1/D9/T3 | validate the user input at server | AKS+DY | incomplete | 2018-11-04
|  | SB1/D9/T4 | testing of module on localhost | DY | incomplete | 2018-11-06
|  | SB1/D10/T1 |  |  | incomplete
|  | SB1/D10/T2 |  |  | incomplete
|  | SB1/D10/T3 |  |  | incomplete
|  | SB1/D10/T4 |  |  | incomplete
|  | SB1/D10/T5 |  |  | incomplete
SB1/US13 |  | SB1/D11/T2 |  |  | incomplete
|  | SB1/D11/T3 |  |  | incomplete
|  | SB1/D11/T4 |  |  | incomplete
|  | SB1/D11/T5 |  |  | incomplete
SB1/US14 |  | SB1/D12/T1
SB1/D12/T2
SB1/D12/T3
SB1/D12/T4
SB1/US15 |  | SB1/D13/T1
SB1/D13/T2
SB1/D13/T3
SB1/D13/T4
SB1/D13/T5
TEAM MEMBER
ADITYA KUMAR SHARMA
DEEPTI YADAV

## SB Hours 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the software so that Wii-mote can be placed on the screen | Search about the software setup | AKS | incomplete | 2 | 60
|  | Search about material required | DY | incomplete | 6 | 60
|  | Purchase hosting | AKS | incomplete | 2 | 60
|  | Develop the software | DY | incomplete | 1 | 60
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search quick quiz application | AKS+DY | incomplete | 4 | 60
|  | quiz app application | DY | incomplete | 2 | 60
|  | search video of many online quiz application | AKS | incomplete | 1 | 60
|  | search audio recording applications | DY | incomplete | 3 | 60
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials | AKS+DY | incomplete | 2 | 60
|  | Study tutorials | AKS | incomplete | 3 | 60
|  | start with Basics of java | DY | incomplete | 1 | 60
|  | start with Basics of java | AKS+DY | incomplete | 2 | 60
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of java | AKS | incomplete | 5 | 60
|  | start with Basics of java | DY | incomplete | 1 | 60
|  | coding of onscreen application | AKS+DY | incomplete | 1 | 60 | 0
|  | coding of onscreen application | AKS | incomplete | 5 | 60 | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application | DY | incomplete | 6 | 60 | 0
|  | coding of onscreen application | AKS+DY | incomplete | 3 | 60 | 0
|  | Debug the code | AKS | incomplete | 2 | 60
|  | Debug the code | DY | incomplete | 4 | 60
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen. | AKS+DY | incomplete | 2 | 60
|  | Implentation of application on virtual screen. | DY | incomplete | 4 | 60
|  | Implentation of application on virtual screen. | AKS | incomplete | 4 | 60
|  | Implentation of application on virtual screen. | DY | incomplete | 3 | 60
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen | AKS | incomplete | 3 | 60
|  | Interface it with PC/laptop | AKS+DY | incomplete | 3 | 60
|  | Switch on the projector and set the projected screen | DY | incomplete | 4 | 60
|  | Interface it with PC/laptop | AKS | incomplete | 3 | 60
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen | DY | incomplete | 5 | 60
|  | Use different applications on the virtual screen | AKS+DY | incomplete | 6 | 60
|  | Check the changes made at the virtual screen | AKS | incomplete | 5 | 60
|  | Checking if it is working effectively with the laptop and not damaged | DY | incomplete | 3 | 60
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables | DY | incomplete | 2 | 60
|  | Prepare all software deliverables | AKS | incomplete | 1 | 60
|  | Prepare a hardware & software guide | AKS+DY | incomplete | 3 | 60
|  | Prepare a user manual & guide for the users | DY | incomplete | 3 | 60
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project | AKS | incomplete | 2 | 60
|  | Project demonstration | AKS+DY | incomplete | 1 | 60
|  | Project demonstration | DY | incomplete | 2 | 60
|  | Project to be operated by different users | AKS | incomplete | 1 | 60
| DY | DEEPTI YADAV
| AKS | AADITYA KUMAR SHARMA
Verified By:
(Product Owner)

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-08-20 | 20 | 0 | Tasks
2018-09-12 | 20 | 0
2018-09-11 | 20 | 0
2018-09-14 | 20 | 0
2018-09-16 | 20 | 0
2018-09-20 | 20 | 0
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <Digital College>
sb2/us1 | Download answer key | SB2/D1/T1 | Designing the GUI | AKS | incomplete | 2018-11-01
|  | SB2/D1/T2 | Connection with database to fetch the data | DY | incomplete | 2018-11-02
|  | SB2/D1/T3 | Testing of the module on localhost and then on server. | AKS+DY | incomplete | 2018-11-03
sb2/us2 | change the password | SB2/D2/T1 | Designing of GUI | AKS | incomplete | 2018-11-04
|  | SB2/D2/T2 | Validating user input at client level | RM | incomplete | 2018-11-05
|  | SB2/D2/T3 | Validating user input at server level | DY | incomplete | 2018-11-06
|  | SB2/D2/T4 | Connection with Database to insert the record. | AKS | incomplete | 2018-11-07
sb2/us3 | share the app | SB2/D3/T1 | Designing of Email(to be send) | AKS | incomplete | 2018-11-09
|  | SB2/D3/T2 | Send Email via coding using the Mandrill App | DY | incomplete | 2018-11-10
|  | SB2/D3/T3 | Connection with database to update the status in the database. | AKS | incomplete | 2018-11-11
|  | SB2/D3/T4 | Testing of the module on localhost and then on server. | AKS+DY | incomplete | 2018-11-12
sb2/us4 | rate the app | SB2/D4/T1 | Designing of GUI | AKS | incomplete | 2018-11-13
|  | SB2/D4/T2 | Validating user input at client level | DY | incomplete | 2018-11-14
|  | SB2/D4/T3 | Validating user input at server level | AKS | incomplete | 2018-11-15
|  | SB2/D4/T4 | Connection with Database to insert the record. | DY | incomplete | 2018-11-16
|  | SB2/D4/T5 | Testing of the module on localhost and then on server. | AKS+DY | incomplete | 2018-11-17
sb2/us5 | feedback from students | SB2/D5/T1 | Designing of Email(to be send) | AKS | incomplete | 2018-11-18
|  | SB2/D5/T2 | Send Email via coding using the Mandrill App | DY | incomplete | 2018-11-19
|  | SB2/D5/T3 | Connection with database to update the status in the database. | AKS | incomplete | 2018-11-20
|  | SB2/D5/T4 | Testing of the module on localhost and then on server. | AKS+DY | incomplete | 2018-11-21
sb2/us6 | about the app | SB2/D6/T1 | Designing of GUI | AKS | incomplete | 2018-11-22
|  | SB2/D6/T2 | Validating user input at client level | DY | incomplete | 2018-11-23
|  | SB2/D6/T3 | Validating user input at server level | DY | incomplete | 2018-11-24
|  | SB2/D6/T4 | Connection with Database to insert the record. | AKS | incomplete | 2018-11-25
|  | SB2/D6/T5 | Testing of the module on localhost and then on server. | AKS | incomplete | 2018-11-25
sb2/us7 | logout | SB2/D7/T1 | Designing of GUI | AKS | incomplete | 2018-11-26
|  | SB2/D7/T2 | Validating user input at client level | AKS+DY | incomplete | 2018-11-27
|  | SB2/D7/T3 | Validating user input at server level | DY | incomplete | 2018-11-28
|  | SB2/D7/T4 | Connection with Database to insert the record. | DY | incomplete | 2018-11-29
|  | SB2/D7/T5 | Testing of the module on localhost and then on server. | AKS+DY | incomplete | 2018-11-29
sb2/us8 | hobby | SB2/D8/T1 | Designing of Email(to be send) | AKS | incomplete | 2018-11-30
|  | SB2/D8/T2 | Send Email via coding using the Mandrill App | AKS | incomplete | 2018-12-01
|  | SB2/D8/T3 | Connection with database to update the status in the database. | DY | incomplete | 2018-12-02
|  | SB2/D8/T4 | Testing of the module on localhost and then on server. | AKS+DY | incomplete | 2018-12-05

## SB Hours 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to download the answere key | designing Gui | AKS | incomplete | 1 | 30
|  | connection the database to fetch data | DY | incomplete | 2 | 30
|  | testing module on locaal host | AKS | incomplete | 5 | 30
|  | designing og gui | DY | incomplete | 4 | 30
2 | change the password | designing Gui | AKS+DY | incomplete | 3 | 30
|  | connection the database to fetch data | AKS | incomplete | 2 | 30
|  | testing module on locaal host | AKS+DY | incomplete | 1 | 30
|  | designing og gui | DY | incomplete | 3 | 30
3 | share the app | designing Gui | AKS | incomplete | 5 | 30
|  | connection the database to fetch data | DY | incomplete | 3 | 30
|  | testing module on locaal host | AKS+DY | incomplete | 2 | 30
|  | designing og gui | DY | incomplete | 4 | 30
4 | rate the app | Designing of GUI | AKS+DY | incomplete | 3 | 30
|  | Validating user input at client level | AKS | incomplete | 2 | 30
|  | Validating user input at server level | DY | incomplete | 1 | 30
|  | Connection with Database to insert the record. | AKS | incomplete | 6 | 30
5 | feedback from students | designing of gui | DY | incomplete | 3 | 30
|  | validition of client level | AKS+DY | incomplete | 4 | 30
|  | testing modules of localhost | AKS | incomplete | 2 | 30
|  | validition of cserverlevel | DY | incomplete | 5 | 30
6 | about the app | designing of gui | AKS | incomplete | 3 | 30
|  | validition of client level | DY | incomplete | 2 | 30
|  | testing modules of localhost | AKS+DY | incomplete | 5 | 30
|  | validition of cserverlevel | AKS+DY | incomplete | 1 | 30
7 | logout | designing of gui | AKS+DY | incomplete | 4 | 30
|  | validition of client level | AKS | incomplete | 3 | 30
|  | testing modules of localhost | DY | incomplete | 2 | 30
|  | validition of cserverlevel | AKS | incomplete | 1 | 30
8 | hobby | designing of gui | DY | incomplete | 2 | 30
|  | validition of client level | AKS+DY | incomplete | 3 | 30
|  | testing modules of localhost | AKS | incomplete | 4 | 30
|  | validition of cserverlevel | DY | incomplete | 3 | 30
9 | update the question | designing of gui | AKS+DY | incomplete | 2 | 30
|  | validition of client level | DY | incomplete | 1 | 30
|  | testing modules of localhost | AKS+DY | incomplete | 2 | 30
|  | validition of cserverlevel | AKS | incomplete | 3 | 30
10 | change the question | designing of gui | DY | incomplete | 4 | 30
|  | validition of client level | AKS | incomplete | 5 | 30
|  | testing modules of localhost | DY | incomplete | 5 | 30
|  | validition of cserverlevel | AKS | incomplete | 4 | 30
| AKS | AADITYA KUMAR SHARMA
| DY | DEEPTI YADAV
Verified By:
(Product Owner)

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-09-25 | 20 | 0 | Tasks
2017-09-28 | 20 | 0
2017-10-02 | 20 | 0
2017-10-05 | 20 | 177
2017-10-07 | 20 | 177
2017-10-09 | 20 | 177
0
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <Digital College>

## SB Hours 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2018-10-16 | 120 | 120 | Tasks
2018-10-18 | 110 | 120
2018-10-20 | 80 | 120
2018-10-21 | 25 | 120
2018-10-22 | 15 | 120
2018-10-23 | 0 | 120
0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - <Digital College>

## SB Hours 04
Sprint Backlog 4
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2019-01-10 | 190 | 190 | Tasks
2019-01-11 | 110 | 190
2019-01-12 | 80 | 190
2019-01-13 | 25 | 190
2019-01-14 | 15 | 190
2019-01-15 | 0 | 190
0
Days